## Planning Form
The Cooperator EXPOS Tradeshow Productivity Management Tool
Company Name
14 Weeks Prior to Show Date | Plan Information
|  | Prepared By |  |  |  | Date Prepared |  |  |  |  | 2018-05-03
Tradeshow Information
|  | Show Name |  |  |  | Setup Dates/Times
|  | Show Organizer & Contact Name |  |  |  | Exhibit Hall Dates/Times
|  | Show Venue |  |  |  | Dismantle Dates/Times
|  | Booth # |  |  |  | Booth Size
|  | Target Attendee Description |  |  |  | Expected # of Target Attendees
Show Notes
Show Budget/Investment
|  |  | Description |  | Budget |  |  |  | Actual |  |  |  | (Over) / Under Budget
|  |  | Booth Space |  | 0 |  |  |  | 0 |  |  |  | 0
Show Services:
|  |  | Furnishings & Carpet |  | 0 |  |  |  | 0 |  |  |  | 0
|  |  | Electrical |  | 0 |  |  |  | 0 |  |  |  | 0
|  |  | Internet |  | 0 |  |  |  | 0 |  |  |  | 0
|  |  | Exhibit & Graphics |  | 0 |  |  |  | 0 |  |  |  | 0
|  |  | Shipping |  | 0 |  |  |  | 0 |  |  |  | 0
|  |  | Lead Retrieval |  | 0 |  |  |  | 0 |  |  |  | 0
Staffing: (50 sq. feet per staffer rule of thumb)
|  |  | Salaries |  | 0 |  |  |  | 0 |  |  |  | 0
|  |  | Temporary Staff |  | 0 |  |  |  | 0 |  |  |  | 0
|  |  | Transportation |  | 0 |  |  |  | 0 |  |  |  | 0
|  |  | Meals |  | 0 |  |  |  | 0 |  |  |  | 0
|  |  | Attire |  | 0 |  |  |  | 0 |  |  |  | 0
Promotion:
|  |  | Giveaways |  | 0 |  |  |  | 0 |  |  |  | 0
|  |  | Pre-Show Promotion to Attendees |  | 0 |  |  |  | 0 |  |  |  | 0
|  |  | Sponsorship |  | 0 |  |  |  | 0 |  |  |  | 0
|  |  | Other |  | 0 |  |  |  | 0 |  |  |  | 0
|  |  | Total |  | 0 |  |  |  | 0 |  |  |  | 0
SMART Exhibiting Goals Specific - Measurable - Action Oriented - Realistic - Time Bound
| Goal # |  | Be careful not to type over formulas. Enter information in cells with red text only. |  |  |  | Calculation |  |  | Goal |  |  |  |  | Actual
| 1 |  | Exhibit Interaction Capacity:
|  |  | Total Exhibit Hours |  |  |  | 7.5
|  |  | x Full-Time Exhibit Staff (50 sq. feet per staffer rule of thumb) |  |  |  | 2
|  |  | = Total Staff Hours |  |  |  | 15
|  |  | x Interactions per Hour per Staffer (3 convervative, 4 moderate, 5 aggressive) |  |  |  | 4
|  |  | = Exhibit Interaction Capacity |  |  |  | 60 |  |  | 60 |  |  |  |  | 0
|  |  | % of Interactions that Convert to a Lead |  |  |  | 25% |  |  | 15 |  |  |  |  | 0
|  |  | % of Leads that Convert to a Sale |  |  |  | 20% |  |  | 3 |  |  |  |  | 0
|  |  | Average Sale Amount |  |  |  | 2000
|  |  | Revenue Target/Potential Value of Leads | [6 empty] | 6000 |  |  |  |  | 0
| 2 |  | Marketing/Brand Awareness Goal
| 3 |  | Customer Relationship Management Goal
| 4 |  | Other?
Featured Products/Services Hierarchy: 1. New Products 2. Addresses Top of the Mind Issue 3. Bread & Butter Products
|  |  | Product/Service | Situations That Create a Need | Features/Benefits |  |  |  | Show Special |  |  |  | Sales Support Materials
1
2
3
12 Weeks Prior | Pre-Show Marketing Plan
| Next Actions - Add more rows if needed. | [6 empty] | Owner/Involved |  | Budget |  |  |  | Due Date |  | Done?
| 1 |  | Compile target visitor list: in-house (C/P/S) and external sources.
> Contact Sales: create Customer/Prospect/Suspect list
> Contact show organizer for FREE pre-reg lists with Product Interest
| 2 |  | Create compelling marketing message and select graphic images.
> Using situations that crate a need/interest, write questions/hooks for marketing
| 3 |  | Design an integrated marketing campaign that delivers at least 3 direct touches to your ideal visitors. Use Email/Web/Social Media/Print/Mail, etc.
| 4 |  | Evaluate and select show marketing media and sponsorships. Use a mix of one-to-one and one-to-many media formats.
| 5 |  | Order promotional products/giveaways.
| 6 |  | Launch pre-show marketing plan. (8 weeks prior)
| 7 |  | Maintain a list of appointments and verbal commitments. (until show time)
8
10 Weeks Prior | Exhibit Staff
| Next Actions - Add more rows if needed. | [6 empty] | Owner/Involved |  | Budget |  |  |  | Due Date |  | Done?
| 1 |  | Determine staffing plan: # of staff, (50 sq ft/staffer rule) department mix (sales, marketing, technical, management, other?), define roles and responsibilities
| 2 |  | Order booth staff attire.
| 3 |  | Depending on the type of show, consider hiring professional talent to provide product samples, answer general questions, and/or attract attendees to your exhibit.
| 4 |  | Provide exhibit staff training with internal staff or hire professional trainer.
| 5 |  | Visit show's Exhibitor website and review educational materials, if any. Forward website link to staff, if applicable. (12 weeks prior)
| 6 |  | Register all booth staff - employees and hired talent. (8 weeks prior)
| 7 |  | Conduct pre-show staff meeting and training session. (1 week prior)
8
Presentation/Demonstration
| Next Actions - Add more rows if needed. | [6 empty] | Owner/Involved |  | Budget |  |  |  | Due Date |  | Done?
| 1 |  | Given spotlighted product/service and its features/benefits, how can visitors interact with the product to learn about features/benefits?
| 2 |  | Select type of presentation: Live Product/Service Demonstration, 1 to 1 or 1 to many? Theater, Video, Interactive Information Stations, Gamification, Scale Models, Other?
| 3 |  | Determine how information will be distributed: product literature, iPad stations, other?
| 4 |  | Prepare presentation staff scripts.
5
8 Weeks Prior | Lead Management
| Next Actions - Add more rows if needed. | [6 empty] | Owner/Involved |  | Budget |  |  |  | Due Date |  | Done?
| 1 |  | Identify lead qualification criteria.
> Convert to questions and order into flow of conversation.
> Define what constitutes an A-B-C lead.
| 2 |  | Determine how lead information will be captured (paper/electronic).
| 3 |  | Order show's lead capture system, or create a hand-held opportunity card.
| 4 |  | Determine lead follow-up plan.
> Give/send info, emaill, mail, social media, phone, in-person
| 5 |  | Create follow-up copy/graphics.
6
Travel Plans (if applicable)
| Next Actions - Add more rows if needed. | [6 empty] | Owner/Involved |  | Budget |  |  |  | Due Date |  | Done?
| 1 |  | Determine staff travel dates.
| 2 |  | Make air reservations, if necessary.
| 3 |  | Make hotel reservations. Note cancellation penalty date.
| 4 |  | Make restaurant reservations.
5
4 Weeks Prior | Progress Check
| Next Actions - Add more rows if needed. | [10 empty] | Owner/Involved |  |  |  | Done?
| 1 |  | Update show budget and actual.
| 2 |  | Check on exhibit, graphics and printed materials.
| 3 |  | Assemble your exhibit and make last minute adjustments, if needed.
| 4 |  | Check on pre-show marketing plan progress.
5
Show Time! | At-Show
| Next Actions - Add more rows if needed. | [10 empty] | Owner/Involved |  |  |  | Done?
| 1 |  | Supervise exhibit set-up. Take photos.
| 2 |  | Test presentation/demonstrations and practice.
| 3 |  | Collect leads at end of shift or end of each day and compare to goal.
4
After | Post-Show
| Next Actions - Add more rows if needed. | [10 empty] | Owner/Involved |  |  |  | Done?
| 1 |  | Exhibit dismantle.
| 2 |  | Hold a post-show recap meeting with appropriate staff. Discuss what worked, what didn't, what was learned.
| 3 |  | Enter leads into CRM system, assign to appropriate people, send requested information, begin lead follow-up.
| 4 |  | Check on lead progress/sales conversion at three predetermined time periods. (30/60/90 or 45/90/180 days)
Analyze Performance
| Next Actions - Add more rows if needed. | [10 empty] | Calculation
| 1 |  | Update show budget and actual above.
> If over/under budget, where and why?
| 2 |  | Update show goals and actual above.
> If goals were not met, why?
| 3 |  | Customers/Prospects Met With, Results, Next Actions:
| 4 |  | Exhibit Attraction Efficiency:
|  |  | Actual # of Exhibit Interactions | [8 empty] | 0
|  |  | / Exhibit Interaction Capacity | [8 empty] | 60
|  |  | = Exhibit Attraction Efficiency | [8 empty] | 0%
| 5 |  | Cost Per Interaction:
|  |  | Total Show Investment | [8 empty] | 0
|  |  | / Actual # of Exhibit Interactions | [8 empty] | 0
|  |  | = Cost Per Interaction | [8 empty] | 0
| 6 |  | Cost Per Lead:
|  |  | Total Show Investment | [8 empty] | 0
|  |  | / Actual # of Leads | [8 empty] | 0
|  |  | = Cost Per Lead | [8 empty] | 0
| 7 |  | Top Line Revenue Return on Investment:
|  |  | Revenue from Converted Leads | [8 empty] | 0
|  |  | Less Total Show Investment | [8 empty] | 0
|  |  | Net Exhibit Gross Profit | [8 empty] | 0
|  |  | / Total Show Investment | [8 empty] | 0
|  |  | = Return on Investment | [8 empty] | 0%
| 8 |  | Rate Your Satisfaction With the Show (1 Low - 10 High) | [8 empty] | 0
Do Again? (Y/N)
Increase Investment? (Y/N)
| 9 |  | Top 3 Lessons For Next Show: